## Defect Summary
DEFECT TRACKER - SUMMARY
Category | Total Defects | Fixed | % Resolved
By Module | 0 | 0
PDF Export | 5 | 5 | 100
Configuration | 5 | 5 | 100
Neo4j Import | 4 | 4 | 100
Streamlit UI | 4 | 4 | 100
SQLite Database | 4 | 4 | 100
Data Transformation | 3 | 3 | 100
Upload Pipeline | 3 | 3 | 100
Entity Extraction | 2 | 2 | 100
Step 3 – Embeddings | 2 | 2 | 100
Step 7 – Evaluation | 2 | 2 | 100
Memory System | 2 | 2 | 100
Relationship Extraction | 1 | 1 | 100
Triple Extraction | 1 | 1 | 100
Step 1 – Neo4j Fetch | 1 | 1 | 100
Step 2 – Text Conversion | 1 | 1 | 100
Step 4 – FAISS Store | 1 | 1 | 100
Step 5 – Query Retrieval | 1 | 1 | 100
Step 6 – LLM Answer | 1 | 1 | 100
Irrelevance Detection | 1 | 1 | 100
TOTAL | 44 | 44 | 100.0%
By Defect Type | 0 | 0
Logic Error | 13 | 13 | 100.0%
Runtime Error | 9 | 9 | 100.0%
Data Error | 7 | 7 | 100.0%
Configuration | 6 | 6 | 100.0%
UI/UX Bug | 5 | 5 | 100.0%
Performance | 2 | 2 | 100.0%
Integration Error | 1 | 1 | 100.0%
Import Error | 1 | 1 | 100.0%
By Severity | 0 | 0
Critical | 6 | 6 | 100.0%
High | 20 | 20 | 100.0%
Medium | 15 | 15 | 100.0%
Low | 3 | 3 | 100.0%

## Defect Details
DETAILED DEFECT LOG
Defect ID | Module | Description | Sprint | Type | Severity | Action Taken | Remarks | Status
D-001 | Data Transformation | Abstract section not detected for papers where abstract was labelled as 'Summary' instead of 'Abstract' | 1 | Logic Error | Medium | Updated section detection regex to include alternate labels such as Summary, Overview and Introduction | Affected 2 out of 10 papers; fixed by broadening the pattern matcher | Fixed
D-002 | Data Transformation | Citation data JSON contained duplicate citation entries for papers that referenced the same source multiple times | 1 | Data Error | Low | Added deduplication step using set-based filtering before writing to citation_data.json | Duplicates inflated citation count; resolved without data loss | Fixed
D-003 | Data Transformation | core_data.json was written with non-UTF-8 characters causing json.load() to fail on Windows machines | 1 | Runtime Error | High | Added ensure_ascii=False and explicit UTF-8 encoding in all json.dump() calls | Impacted portability of JSON files across platforms | Fixed
D-004 | Entity Extraction | spaCy NER model failed to load with error 'Can't find model en_core_web_sm' on fresh environment setup | 1 | Configuration | High | Added python -m spacy download en_core_web_sm to the installation instructions and setup script | Missing model caused complete failure of entity_extraction.py; added to README | Fixed
D-005 | Entity Extraction | Entity extraction produced empty output for papers where all text was stored as a single long string with no sentence boundaries | 1 | Logic Error | Medium | Added sentence tokenisation using spaCy sentencizer before NER processing | Affected 1 paper; post-fix entity count increased from 0 to 47 for that paper | Fixed
D-006 | Relationship Extraction | relationship_extraction.py raised KeyError when a chunk had no 'text' key due to incomplete JSON entry | 1 | Runtime Error | High | Added defensive dict.get() checks with empty string fallback before processing each chunk | Caused script to crash mid-run; fixed with input validation | Fixed
D-007 | Triple Extraction | Some triples had None as subject or object when entity spans were empty strings after stripping whitespace | 1 | Data Error | Medium | Added validation to skip any triple where subject, predicate or object is None or empty | Invalid triples would have caused Cypher import errors in Neo4j | Fixed
D-008 | Neo4j Import | neo4j_import.py raised AuthError: Unauthorized when correct password was entered due to trailing whitespace in config | 2 | Configuration | High | Added .strip() to all credential reads from config.py; documented that password must have no spaces | Blocked entire import phase; required environment variable sanitisation | Fixed
D-009 | Neo4j Import | Running neo4j_import.py twice on same data created duplicate nodes because CREATE was used instead of MERGE | 2 | Logic Error | High | Replaced all CREATE statements with MERGE using paper_id and entity name as unique identifiers | Caused node count to double on re-import; MERGE resolved idempotency | Fixed
D-010 | Neo4j Import | Section nodes were created with empty raw_text property because paper text was stored under a different key in graph_documents.json | 3 | Data Error | High | Wrote fix_all_sections.py and fix_empty_sections.py to backfill raw_text from source JSON into all Section nodes | Affected all 10 papers; required a separate patching script to repair the graph | Fixed
D-011 | Neo4j Import | Neo4j connection timed out during bulk import of large papers because transaction batch size was too large | 3 | Performance | Medium | Reduced batch size from 1000 to 100 nodes per transaction and added retry logic with exponential backoff | Import time increased slightly but stability improved significantly | Fixed
D-012 | Step 1 – Neo4j Fetch | step1_neo4j_fetch.py returned empty graph_documents.json when Neo4j DBMS was started but the database was not yet online | 3 | Integration Error | High | Added a connection health-check loop that retries up to 5 times before raising an error with clear instructions | User had to manually wait for Neo4j to fully start; health-check now handles this automatically | Fixed
D-013 | Step 2 – Text Conversion | Relationship chunks had duplicate content because the same relationship appeared in both directions in Neo4j | 3 | Data Error | Medium | Added seen_pairs set to deduplicate relationship chunk text during conversion | Reduced relationship chunk count and improved retrieval precision | Fixed
D-014 | Step 3 – Embeddings | Python 3.12 raised RuntimeError: can't register atexit after shutdown when sentence-transformers encoded large batches | 3 | Runtime Error | Critical | Upgraded joblib, scikit-learn and sentence-transformers to latest versions via pip install --upgrade | Critical blocker affecting all Python 3.12 environments; resolved by dependency upgrade | Fixed
D-015 | Step 3 – Embeddings | embeddings_matrix.npy shape mismatch caused FAISS index build to fail when one chunk had zero-length text | 3 | Data Error | High | Added text length validation in step2 to skip chunks with fewer than 10 characters before embedding | Zero-length embeddings produced NaN vectors that corrupted the FAISS index | Fixed
D-016 | Step 4 – FAISS Store | FAISS index built with IndexFlatL2 returned low scores for semantically similar queries because embeddings were normalised | 3 | Logic Error | High | Switched from IndexFlatL2 to IndexFlatIP (inner product) which is equivalent to cosine similarity for normalised vectors | Score scale changed from distance to similarity; all thresholds were updated accordingly | Fixed
D-017 | Step 5 – Query Retrieval | Paper filter returned zero results for valid queries because paper_id comparison was case-sensitive and user input was lowercase | 3 | Logic Error | Medium | Added .upper() normalisation on paper_id in both the filter and the metadata comparison | Affected all paper-specific queries when user typed paper ID in lowercase | Fixed
D-018 | Step 6 – LLM Answer | Groq API raised RateLimitError during rapid consecutive queries causing the app to crash with unhandled exception | 3 | Runtime Error | High | Wrapped all Groq API calls in try-except; returns formatted error string instead of raising; added retry hint in UI | Prevented app crash; user now sees a friendly error message with retry guidance | Fixed
D-019 | Step 7 – Evaluation | Faithfulness metric returned 0.0 for all answers because sentence splitting on full stops broke mid-acronym (e.g. U.S.A.) | 3 | Logic Error | Medium | Switched sentence splitting to use a minimum length filter of 20 characters to skip false splits | Faithfulness scores now reflect actual answer quality more accurately | Fixed
D-020 | Step 7 – Evaluation | Recall@K raised ZeroDivisionError when no chunks in the entire index exceeded the relevance threshold for a given query | 3 | Runtime Error | High | Added recall_total > 0 guard before computing recall score; returns None when no relevant total exists | Prevented hard crash during evaluation of edge-case queries | Fixed
D-021 | Upload Pipeline | PDF upload pipeline silently produced empty sections for scanned PDFs because pdfplumber could not extract text from image-based pages | 3 | Logic Error | High | Added page-level text length check; pages with fewer than 50 characters are flagged as scanned and skipped with a warning | Scanned PDFs now produce an informative warning instead of being silently indexed as empty | Fixed
D-022 | Upload Pipeline | FAISS index became corrupted after uploading a paper with embeddings of a different dimension than the existing index | 3 | Data Error | Critical | Added dimension validation before adding new embeddings; raises clear error if model dimension does not match existing index | Critical data integrity issue; dimension check now prevents corruption | Fixed
D-023 | Upload Pipeline | Uploading a paper with an already-existing paper_id overwrote existing metadata entries without warning | 4 | Logic Error | Medium | Added paper_id existence check before processing; shows warning and requires user confirmation to overwrite | Prevented accidental data loss from duplicate uploads | Fixed
D-024 | Streamlit UI | Chat history was lost on every page rerun because chat_history was not initialised in st.session_state before use | 4 | Logic Error | High | Added full session_state defaults dict initialised at the top of main() before any widget rendering | Affected all output modes; fixed by ensuring state persistence across reruns | Fixed
D-025 | Streamlit UI | Output mode radio button reset to default on every interaction because it was not stored in session_state | 4 | UI/UX Bug | Medium | Streamlit radio widgets persist automatically; root cause was a competing st.rerun() call that reset state; removed redundant rerun | Users had to reselect mode after every sidebar interaction | Fixed
D-026 | Streamlit UI | Quick suggestion buttons triggered query twice — once from button click and once from the pending_query pop causing duplicate answers | 4 | Logic Error | High | Changed pending_query handling to use st.session_state.pop() which clears the value after first read preventing double trigger | Duplicate answers appeared in chat history; pop() resolved the race condition | Fixed
D-027 | Streamlit UI | Paper selector dropdown showed stale paper list after a new paper was uploaded because available_papers() was not re-evaluated | 4 | UI/UX Bug | Medium | Added st.rerun() after successful paper upload so the sidebar refreshes and the new paper appears in all dropdowns | Users had to manually refresh the page to see newly uploaded papers | Fixed
D-028 | Irrelevance Detection | General knowledge pattern regex crashed with re.error for queries containing special regex characters such as parentheses and question marks | 4 | Runtime Error | High | Added re.escape() on the user query string before pattern matching to sanitise special characters | Queries like 'what is ReLU(x)?' caused the entire irrelevance check to fail | Fixed
D-029 | Memory System | chat_memory.json grew indefinitely because the MEMORY_MAX trim was applied before appending the new entry instead of after | 4 | Logic Error | Medium | Moved the memory[-MEMORY_MAX:] slice to after the append so the new entry is always included and oldest entries are removed | Memory file could grow without bound; off-by-one in trim logic | Fixed
D-030 | Memory System | Memory similarity search raised ValueError when a stored memory entry had an empty embedding list from a failed encode call | 4 | Runtime Error | Medium | Added if not item.get('embedding') guard to skip entries with missing or empty embeddings during similarity search | Prevented crash on memory lookup; corrupted entries are now safely skipped | Fixed
D-031 | SQLite Database | chat_db.py raised sqlite3.OperationalError: no such table when app launched because init_db() was called after the first DB query | 4 | Logic Error | Critical | Moved db.init_db() call to the very top of main() before any session or message operations | Caused app to crash on first launch; ordering fix resolved the issue completely | Fixed
D-032 | SQLite Database | Loading a past session from the dropdown showed messages in wrong order because get_session_messages() had no ORDER BY clause | 4 | Logic Error | Medium | Added ORDER BY created_at ASC to the messages fetch query in chat_db.py | Messages appeared in random insertion order; chronological ordering now ensured | Fixed
D-033 | SQLite Database | Session message_count showed incorrect value because it was only incremented on save_message() but not decremented when messages were deleted | 4 | Data Error | Low | Replaced stored message_count with a live COUNT(*) subquery formula in get_all_sessions() | Count is now always accurate regardless of deletions | Fixed
D-034 | SQLite Database | Concurrent session saves raised sqlite3.DatabaseError: database is locked under rapid query submission | 4 | Performance | Medium | Added WAL (Write-Ahead Logging) mode via PRAGMA journal_mode=WAL on connection open to allow concurrent reads | WAL mode reduced locking conflicts significantly under normal usage patterns | Fixed
D-035 | PDF Export | ReportLab PDF generation crashed with RuntimeError: can't register atexit after shutdown in Python 3.12 when using HeaderFooterCanvas | 4 | Runtime Error | Critical | Replaced HeaderFooterCanvas override approach with BaseDocTemplate and PageTemplate using onPage callable for headers and footers | Critical blocker on Python 3.12; architectural change to BaseDocTemplate fully resolved the issue | Fixed
D-036 | PDF Export | st.download_button inside st.chat_message() container raised StreamlitAPIException: DuplicateWidgetID on second render | 4 | UI/UX Bug | Critical | Moved all PDF download buttons outside st.chat_message() containers and added hash-based unique key suffix using first 64 bytes of PDF content | Affected every answer with a PDF button; widget placement fix resolved duplicate key errors | Fixed
D-037 | PDF Export | PDF export button rendered inside the st.spinner() context caused widget to disappear after spinner closed | 4 | UI/UX Bug | High | Moved PDF button rendering to after chat_history.append() and outside the spinner block so it persists after generation completes | PDF button was invisible to users after answer generation; placement fix made it consistently visible | Fixed
D-038 | PDF Export | PDF cover page raised KeyError when session had no paper_filter set because the key was accessed directly without a default | 4 | Runtime Error | Medium | Changed all session_info dict accesses to use .get() with appropriate default values such as 'All Papers' | Affected sessions that used All Papers mode; .get() fallback resolved the error | Fixed
D-039 | PDF Export | PDF metrics table overflowed page width for sessions with long answer text because column widths were fixed without checking content length | 4 | UI/UX Bug | Low | Set explicit column widths proportional to content type and enabled text wrapping on all metric cells in the ReportLab table style | Metrics table now fits within the content frame on all page sizes | Fixed
D-040 | Configuration | app.py raised ModuleNotFoundError: No module named 'chat_db' after restructuring project into frontend/ and backend/ folders | 4 | Import Error | Critical | Added sys.path.insert() block at top of app.py to add both project root and backend/ directory to Python path | Structural refactor broke all backend imports; sys.path fix resolved without changing import statements | Fixed
D-041 | Configuration | delete_paper() saved embeddings_matrix.npy to the current working directory instead of the data/ folder after folder restructure | 4 | Configuration | High | Replaced hardcoded filename string with config.EMBEDDINGS_FILE absolute path reference | Caused embeddings file to be written to wrong location; config centralisation prevented recurrence | Fixed
D-042 | Configuration | FAISS index file path resolved differently depending on which directory streamlit run was executed from causing FileNotFoundError | 4 | Configuration | High | Centralised all file paths in config.py using os.path.abspath(__file__) as root anchor; all paths are now absolute | Affected all file reads and writes; absolute path pattern fully eliminates working-directory dependency | Fixed
D-043 | Configuration | data/ directory did not exist on fresh clone causing all file write operations to fail with FileNotFoundError: [Errno 2] | 4 | Configuration | High | Added os.makedirs(DATA_DIR, exist_ok=True) in config.py so the data folder is created automatically on first import | Affected all first-time setup scenarios; auto-creation resolved the onboarding friction | Fixed
D-044 | Configuration | chat_db.py used a relative path for DB_FILE causing the SQLite database to be created in whatever directory the app was launched from | 4 | Configuration | High | Added sys.path and config import to chat_db.py; DB_FILE now uses config.DB_FILE absolute path | Database location was inconsistent across different launch directories; absolute path fixed the issue | Fixed