## Agile Summary
AGILE WORKFLOW - DASHBOARD
SPRINT METRICS
Metric | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
User Stories | 1 | 2 | 4 | 5
Stand-ups | 1 | 1 | 5 | 5
Status | Completed | Completed | Completed | In Progress

## Product Backlog
PRODUCT BACKLOG
Planned Sprint | Actual Sprint | User Story | MOSCOW | Dependency | Assignee | Status
1 | 1 | get 10-20 research papers for the data collection |  | - |  | 3- Completed
1 | 2 | convert the contents of the research papers into 4 types of data such as core data,abstract data, metadata and citation data then store it in 4 .json files |  | 1 |  | 3- Completed
2 | 2 | Create entity extraction, relationship extraction and triples of the research papers data which is stored in 4 json files |  | 2 |  | 3- Completed
2 | 2 | Import all extracted entities, relationships and triples into Neo4j graph database by creating nodes, edges and properties using Cypher queries |  | 2 |  | 3- Completed
3 | 3 | Query Neo4j using 7 Cypher queries to pull graph documents and store the results in graph_documents.json for downstream processing |  | 2 |  | 3- Completed
3 | 3 | Convert graph documents into 4 chunk types such as section, relationship, citation and metadata chunks totalling 165 chunks and store in text_chunks.json |  | 2 |  | 3- Completed
3 | 3 | Generate 384-dimension sentence embeddings for all chunks using all-MiniLM-L6-v2 model and store in embeddings_matrix.npy and chunk_embeddings.json |  | 2 |  | 3- Completed
3 | 3 | Build a FAISS vector index from the embeddings and store the index in faiss_index.bin and the position-to-chunk mapping in faiss_metadata.json |  | - |  | 3- Completed
3 | 3 | Implement query embedding, FAISS similarity search with paper filter, score threshold, deduplication and top-K chunk retrieval |  | - |  | 3- Completed
3 | 3 | Integrate Groq API with llama-3.1-8b-instant model and build structured prompt builder to generate RAG answers from retrieved chunks |  | - |  | 3- Completed
3 | 3 | Implement 5 evaluation metrics such as Confidence, Precision@K, Recall@K, Semantic Similarity and Faithfulness to measure answer quality |  | - |  | 3- Completed
3 | 3 | Wire all the process into a single terminal-runnable end-to-end pipeline with progress |  | - |  | 3- Completed
4 | 4 | Build a full paper upload pipeline that handles PDF, DOCX and TXT parsing, section extraction, NER, triples, Neo4j import, chunk generation, embedding and FAISS index update |  | 3 |  | 3- Completed
4 | 4 | Build the Streamlit chat interface with FAISS retrieval, Groq LLM integration, paper selector dropdown, 6 output modes, persistent Q&A memory, 2-stage irrelevance filter, slash commands, custom CSS, sidebar controls for paper upload and delete, Stop Generation button and Quick Action buttons |  | 3 |  | 3- Completed
4 | 4 | Build SQLite persistence layer with sessions and messages tables, WAL mode, session CRUD, message save and fetch, selected message export, DB stats and full session management in sidebar including New Chat, session switcher, Rename and Delete controls |  | 3 |  | 3- Completed
4 | 4 | Build PDF export engine using ReportLab with branded header and footer, cover metadata table, colour-coded section bars, metrics table and source citations, and integrate PDF download buttons in sidebar for full session or selected messages and inline after each answer |  | 3 |  | 3- Completed

## Stand-up Meetings
DAILY STAND-UP MEETINGS
Sprint | Day | Impediments | Action Taken
1 | 27th Jan | Data Collection for the model | Begin the work of milestone 1
2 | 28h Jan | Review of collected data | verified the collected data
3 | 30th Jan | Entity extraction, relationship extraction and Triples from collected data | Begin the work of completing milestone 1
4 | 2nd Feb | Review of milestone 1 | verified the completed work
5 | 3rd Feb | Review of milestone 1 | verified the completed work
6 | 4th Feb | Review of milestone 1 | verified the completed work
7 | 6th Feb | Download Neo4j and Create knowledge graph by studying about it | Begin the work for milestone 2
8 | 10th Feb | Review of milestone 2 | verified the completed work
10 | 11th Feb | Review of milestone 2 | verified the completed work
11 | 13th Feb | Review of milestone 2 | verified the completed work
12 | 16th Feb | Review of milestone 2 | verified the completed work
13 | 17th Feb | Implementation of RAG Pipeline | Begin the work for milestone 3
14 | 18th Feb | Doubt clarification regarding RAG pipeline implementation | Study about the milestone 3
15 | 19th Feb | Doubt clarification regarding RAG pipeline implementation | Study about the milestone 3
16 | 20th Feb | Doubt clarification regarding RAG pipeline implementation | Study about the milestone 3
17 | 23rd Feb | Review of milestone 3 and beginning of developing frontend for the created backend | verified the completed work and begin the work of milestone 4
18 | 24th Feb | Review of milestone 3 | verified the completed work
19 | 25th Feb | Review of milestone 3 | verified the completed work
20 | 26th Feb | Review of milestone 4 | verified the completed work
21 | 27th Feb | Mock Final presentation and requirement to be completed in the project | Presentation of the entire work
22 | 28th Feb | Review of milestone 4 | Verify the completed work
23 | 2nd Mar | Review of milestone 4 | Verify the completed work
24 | 3rd Mar | Review of milestone 4 | Verify the completed work
25 | 4th Mar | Review of milestone 4 | Verify the completed work

## Retrospectives
SPRINT RETROSPECTIVES
Sprint # | Start Date | End Date | Start Doing | Stop Doing | Continue Doing | Action Taken
3 | 2026-02-04 | 2026-02-11 | environment validation at the beginning of every pipeline step by checking that all required files such as faiss_index.bin, graph_documents.json, and text_chunks.json exist before the step runs, so that missing file errors are caught early with a clear message instead of crashing mid-pipeline. | Stop using hardcoded relative file paths like "faiss_index.bin" and "embeddings_matrix.npy" directly in scripts, because these resolve to whatever directory the script is run from and cause FileNotFoundError when the working directory changes. | Continue using config.py as the single source of truth for all file paths, model names, API keys, and RAG parameters, because centralising configuration eliminates path resolution bugs and makes the project portable across different machines and directories. | Replaced all hardcoded relative file path strings with absolute path references from config.py using os.path.abspath(__file__) as the root anchor, so that all file reads and writes resolve correctly from any working directory.
3 | 2026-02-04 | 2026-02-11 | input sanitisation on all user queries before they reach the regex pattern matcher and the FAISS search, including escaping special characters like parentheses and question marks, to prevent runtime errors on unconventional queries. | Stop using CREATE in Cypher import queries and replace all occurrences with MERGE, because running the import script more than once with CREATE doubles all nodes and edges in the graph, corrupting the knowledge base. | Continue using MERGE in all Cypher queries for Neo4j import now that it has been adopted, because it guarantees idempotent imports and allows the pipeline to be re-run safely without duplicating graph data. | Replaced all CREATE statements in neo4j_import.py with MERGE using paper ID and entity name as unique identifiers, eliminating duplicate nodes and making the import script safely re-runnable.
3 | 2026-02-04 | 2026-02-11 | dimension validation before adding new embeddings to the FAISS index during paper uploads, so that any mismatch between the new paper's embedding size and the existing index is caught immediately and does not silently corrupt the vector store. | Stop calling db.init_db() after session or message operations in the app, because the database tables must exist before they are queried and placing the init call late causes the app to crash on first launch. | Continue using IndexFlatIP for the FAISS vector store with normalised embeddings, because inner product search on L2-normalised vectors is mathematically equivalent to cosine similarity and gives the most semantically accurate retrieval results. | Wrote fix_all_sections.py and fix_empty_sections.py to backfill the missing raw_text property on all Section nodes in Neo4j that were created without body text during the initial import.
3 | 2026-02-04 | 2026-02-11 | batch size control on all Neo4j import transactions by committing in groups of 100 nodes per transaction instead of sending everything in one large batch, to prevent connection timeouts on large paper imports. | Stop building PDF download buttons inside st.chat_message() containers, because Streamlit raises a DuplicateWidgetID exception when the same widget key appears more than once inside a container on re-render. | Continue using IndexFlatIP for the FAISS vector store with normalised embeddings, because inner product search on L2-normalised vectors is mathematically equivalent to cosine similarity and gives the most semantically accurate retrieval results. | Switched FAISS index type from IndexFlatL2 to IndexFlatIP and updated all score thresholds to reflect similarity rather than distance values, correcting retrieval ranking for normalised embeddings.
4 | 2026-02-12 | 2026-02-26 | unit tests for each individual pipeline step so that regressions in one step are caught before they affect downstream steps like FAISS indexing or LLM generation | Stop overriding the ReportLab canvas class with HeaderFooterCanvas for headers and footers, because this approach is unreliable in ReportLab 4.x and Python 3.12 and causes a RuntimeError: can't register atexit after shutdown on document build. | Continue using BaseDocTemplate with PageTemplate and onPage callables in ReportLab for PDF generation, because this architecture is stable across Python 3.12 and avoids the atexit crash that occurred with the canvas override approach. | Added a chunk text length validation in Step 2 to skip any chunk with fewer than 10 characters before it enters the embedding step, preventing zero-length vectors and NaN values from corrupting the FAISS index.
4 | 2026-02-12 | 2026-02-26 | chunk quality validation in Step 2 by filtering out any chunk with fewer than 10 characters before it enters the embedding pipeline, preventing zero-length embedding vectors that corrupt the FAISS index | Stop trimming the memory list before appending the new entry in the memory system, because this off-by-one error means the most recently asked question is the one most likely to be dropped when the memory cap is reached. | Continue storing PDF download buttons outside st.chat_message() containers with hash-based unique key suffixes, because this pattern reliably prevents duplicate widget key errors across all render cycles. | Upgraded joblib, scikit-learn, and sentence-transformers to their latest versions to resolve the RuntimeError: can't register atexit after shutdown crash that affected all Python 3.12 environments.
4 | 2026-02-12 | 2026-02-26 | a paper duplicate check before processing any upload so that submitting a paper with an existing paper ID does not silently overwrite chunks that are already indexed. | Stop accessing session info dictionary keys directly without .get() fallback defaults, because any session that was created without a paper filter causes a KeyError in the PDF export cover page generation. | Continue using st.session_state.pop() for the pending_query pattern so that quick action buttons and suggestion buttons only fire once and do not cause duplicate answers to appear in the chat history. | Replaced the HeaderFooterCanvas override in pdf_export.py with BaseDocTemplate and PageTemplate using an onPage callable, fully resolving the ReportLab crash on Python 3.12.
4 | 2026-02-12 | 2026-02-26 | version pinning in requirements.txt for all critical packages such as sentence-transformers, faiss-cpu, and reportlab so that the project does not break when upstream packages release breaking changes. | Stop computing session message_count as a stored integer that is only incremented on save, because this count becomes inaccurate whenever messages or sessions are deleted and misleads users in the session dropdown. | Continue using WAL mode for SQLite by setting PRAGMA journal_mode=WAL on every connection, because it significantly reduces database locking errors when the app performs concurrent read and write operations. | Moved all st.download_button PDF widgets outside st.chat_message() containers and added a hash-based unique key suffix derived from the first 64 bytes of the PDF content, eliminating all DuplicateWidgetID exceptions.
4 | 2026-02-12 | 2026-02-26 | Start doing a .gitignore file from day one that excludes .env, all files in the data/ folder, __pycache__, *.bin, *.npy, and *.db so that credentials and large binary files are never accidentally pushed to the repository. | Stop placing the PDF export button inside the st.spinner() context block, because the button disappears as soon as the spinner closes and users cannot find the download option after generation completes. | Continue adding sys.path.insert() at the top of app.py and chat_db.py to add both the project root and the backend/ directory, because this ensures all imports resolve correctly regardless of which directory streamlit run is executed from. | Moved the db.init_db() call to the very top of main() in app.py before any session or message operations, fixing the first-launch crash caused by querying tables that had not yet been created.